## Features
Feature ID | Feature Name | Description | Priority | Status | Assigned To | Created Date | Due Date
F001 | Authentication & User Management | JWT-based login, registration, role-based access control | High | Completed | System | 2024-01-01 | 2024-01-15
F002 | Student Information Management | QR codes, documents, promotion, transfer tracking | High | Completed | System | 2024-01-01 | 2024-02-01
F003 | Teacher & Staff Management | Auto-generated IDs, subject assignment | High | Completed | Admin | 2024-01-01 | 2024-02-01
F004 | Parent Management | Parent-student linking system | Medium | Completed | Admin | 2024-01-15 | 2024-02-15
F005 | Class & Subject Management | Complete academic structure management | High | Completed | Admin | 2024-01-01 | 2024-02-01
F006 | Attendance Management | Daily tracking, bulk marking, reports | High | Completed | Teachers | 2024-02-01 | 2024-02-20
F007 | Examination & Grading | Grade management, report cards, analytics | High | Completed | Teachers | 2024-02-15 | 2024-03-01
F008 | Fees & Finance Management | Fee structures, payments, receipts, accounting | High | Completed | Admin | 2024-02-20 | 2024-03-15
F009 | Analytics Dashboard | Real-time charts, performance statistics | Medium | Completed | All Roles | 2024-03-01 | 2024-03-20
F010 | Audit Logging | Complete activity tracking system | High | Completed | System | 2024-01-01 | 2024-01-10
F011 | Document Upload System | Student document management | Medium | Completed | Admin/Teachers | 2024-02-10 | 2024-03-01
F012 | Export to Excel/PDF | Professional report generation | Medium | Completed | All Roles | 2024-03-01 | 2024-03-15
F013 | Certificate Generation System | Dynamic certificates with QR verification | Medium | Completed | Admin | 2024-03-10 | 2024-03-25
F014 | Certificate Template Management | Customizable certificate templates | Low | Completed | Admin | 2024-03-15 | 2024-03-25
F015 | Communication Module | Announcements, messages, notifications | Medium | Completed | All Roles | 2024-03-20 | 2024-04-01
F016 | Documents Module | Student documents, certificates, templates | Medium | Completed | Admin/Teachers | 2024-03-15 | 2024-04-01
F017 | Inventory Module | Asset management, maintenance tracking | Low | Completed | Admin | 2024-03-25 | 2024-04-05
F018 | Reports Module | Student, attendance, financial, custom reports | Medium | Completed | Admin/Teachers | 2024-03-20 | 2024-04-01
F019 | Assignment Management | File upload system for assignments | Medium | Backend Ready | Teachers | 2024-04-01 | 2024-04-15
F020 | Library Module | Book management system | Low | Pending | Admin | 2024-04-15 | 2024-05-01
F021 | Transport Module | School transport management | Low | Pending | Admin | 2024-04-20 | 2024-05-15
F022 | Hostel Module | Hostel management system | Low | Pending | Admin | 2024-04-25 | 2024-05-20
F023 | Events & Calendar Module | Event scheduling and calendar | Medium | Pending | All Roles | 2024-05-01 | 2024-05-20
F024 | Settings Module | System configuration | Medium | Pending | Admin | 2024-05-01 | 2024-05-15
F025 | Online Admissions | Digital admission process | High | Pending | Admin | 2024-05-15 | 2024-06-01
F026 | ID Card Generation | Student ID cards with photos | Medium | Pending | Admin | 2024-05-20 | 2024-06-01
F027 | Bulk Import | Excel/CSV student import | Medium | Pending | Admin | 2024-05-25 | 2024-06-10
F028 | Teacher Performance Review | Teacher evaluation system | Medium | Pending | Admin | 2024-06-01 | 2024-06-15
F029 | Teacher Payroll | Salary management system | Medium | Pending | Admin | 2024-06-05 | 2024-06-20
F030 | Timetable Management | Class scheduling system | High | Pending | Admin/Teachers | 2024-06-10 | 2024-06-25
F031 | Advanced Analytics | Enhanced reporting features | Medium | Pending | Admin/Teachers | 2024-06-15 | 2024-07-01

## Issues
Issue ID | Feature ID | Issue Title | Description | Severity | Status | Reported By | Reported Date | Resolved Date
I001 | F002 | QR Code Generation Performance | QR code generation is slow for bulk students | Medium | Resolved | Admin | 2024-02-15 | 2024-02-20
I002 | F007 | Grade Calculation Bug | Grade percentage calculation incorrect for some subjects | High | Resolved | Teachers | 2024-03-05 | 2024-03-08
I003 | F008 | Payment Gateway Integration | Online payment not working with some banks | High | In Progress | Admin | 2024-03-20
I004 | F015 | Notification Delivery | Push notifications not delivered to iOS devices | Medium | Open | Users | 2024-04-01

## Validations
Validation ID | Feature ID | Test Case | Expected Result | Actual Result | Status | Tested By | Test Date
V001 | F001 | Login with valid credentials | User should be redirected to dashboard | User redirected successfully | Passed | QA | 2024-01-20
V002 | F001 | Login with invalid password | Error message should be displayed | Error message shown | Passed | QA | 2024-01-20
V003 | F006 | Mark attendance for entire class | All students should be marked present/absent | Attendance marked successfully | Passed | QA | 2024-02-25
V004 | F008 | Process online payment | Payment should be confirmed and receipt generated | Payment processed, receipt generated | Passed | QA | 2024-03-20
V005 | F013 | Generate transfer certificate | Certificate should be generated with QR code | Certificate generated with QR | Passed | QA | 2024-03-30

## ChangeLog
Change ID | Feature ID | Change Description | Change Type | Reason for Change | Implemented By | Implementation Date | Version
C001 | F001 | Added two-factor authentication | Security Enhancement | Improve security | Dev Team | 2024-02-01 | v2.1.0
C002 | F002 | Added bulk student promotion | Feature Enhancement | Reduce manual work for year-end promotion | Dev Team | 2024-02-15 | v2.2.0
C003 | F007 | Improved grade calculation algorithm | Bug Fix | Fix percentage calculation errors | Dev Team | 2024-03-08 | v2.2.1
C004 | F015 | Added email notifications | Feature Enhancement | Keep users informed via email | Dev Team | 2024-03-25 | v2.3.0
C005 | F013 | Added certificate verification system | Feature Enhancement | Verify certificate authenticity via QR | Dev Team | 2024-03-28 | v2.3.1